## Product Backlog
Planned Sprint Modified | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status | Planned Sprint
S1 | S1 | US-001 | BASICS OF PROBABILITY AND STATISTICS [mean,median,mode,harmonic mean,conditional probability,range,variance etc. | SHOULD HAVE | No Dependency | VRUTURAJSINH JADEJA | 3- Completed
S1 | S1 | US-002 | Introduction to project (Chat with Your Document AI) | MUST HAVE | No Dependency | VRUTURAJSINH JADEJA | 3- Completed
S2 | S2 | US-003 | Define project goals and architecture documentation | MUST HAVE | Algorithms | VRUTURAJSINH JADEJA | 3- Completed
S2 | S2 | US-004 | Create a workflow to handle PDF document uploads | SHOULD HAVE | Data | VRUTURAJSINH JADEJA | 3- Completed
S3 | S3 | US-005 | Build a retriever module to split PDFs into chunks | SHOULD HAVE | Ollama | VRUTURAJSINH JADEJA | 3- Completed
S4 | S4 | US-006 | Integrate a local LLM for natural language querying | MUST HAVE | Streamlit | VRUTURAJSINH JADEJA | 3- Completed
S5 | S5 | US-007 | Develop conversational chat interface with Streamlit | MUST HAVE | Python | VRUTURAJSINH JADEJA | 3- Completed
S6 | S6 | US-008 | RAG [Introduction, Data preparation->Raw data Sources, Chuncking, Embeddings,Vector database, LLMs, Response][ Libraries-> langchain community,PyPDF,PyPDFDirectoryLoader,docx2txt,RecursiveCharacterTextSplitter,fastembed,faiss-cpu, db.as_retriever, groq, langchain-groq, python-dotenv, API, Chatgroq, LLM] ,Perform integration testing and deployment | MUST HAVE | Google colab, Streamlit | VRUTURAJSINH JADEJA | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours Modified | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Unnamed: 20 | Unnamed: 21 | Unnamed: 22 | NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 75 | 22 | 12 | 11 | 9 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Introduction to project(Form Filling AI) | 2024-11-04 | 2024-11-06 | Seenu Ananth K | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-02 | Workflow Creation and Project Goal Document | 2024-11-07 | 2024-11-08 | Seenu Ananth K | Design | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-03 | Document Discussion(Agile Template,Defect Tracker,Unit Testing) | 2024-11-11 | 2024-11-11 | Seenu Ananth K | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-04 | Use Case Research and Preparation | 2024-11-12 | 2024-11-15 | Seenu Ananth K | Others | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-05 | Python practice Kit Completion | 2024-11-16 | 2024-11-22 | Seenu Ananth K, Vaibhav Sunil Shimpi, Akshaya | Coding | 3- Completed | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-06 | SQL practice Kit Completion | 2024-11-23 | 2024-11-29 | Seenu Ananth K, Vaibhav Sunil Shimpi, Akshaya | Coding | 3- Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-07 | Project Discussion Module 1(Voice Input and Language Processing) | 2024-12-02 | 2024-12-06 | Seenu Ananth K | Build | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-08 | Project Discussion Module 2(Workflow Automation and Optimization) | 2024-12-09 | 2024-12-13 | Seenu Ananth K | Coding | 2- In Progress | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-09 | Project Discussion Module 3(Integration with existing services) | 2024-12-16 | 2024-12-20 | Seenu Ananth K | Integration Test | 2- In Progress | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TID-10 | Project Discussion Module 4(Testing and Deployment) | 2024-12-23 | 2024-12-27 | Seenu Ananth K | System Test | 2- In Progress | 8 | Day 1: 3; Day 2: 0; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 1; Day 7: 1
| Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy

## Stand up Meeting
Sprint Modified | Day | Impediments | Action Taken | Sprint
Sprint 1 | Day 2 | Lack of clarity on project requirements | Conducted a detailed discussion with mentors and team
Sprint 1 | Day 4 | Lack of clarity on specific project goals and workflow steps. | Conducted a team brainstorming session and reviewed the project requirements.
Sprint 2 | Day 6 | Agile template confusion | Conducted a meeting where all doubts were clarified by the mentor.
Sprint 2 | Day 7 | Difficulty in identifying all potential use cases due to incomplete information. | Conducted additional research and consulted online resources to fill gaps.
Sprint 2 | Day 9 | Confusion about prioritizing use cases for preparation. | Created a priority matrix to evaluate and rank use cases based on importance.
Sprint 3 | Day 12 | Difficulty in debugging Python practice code | Collaborated with Vaibhav and Akshaya to resolve issues
Sprint 4 | Day 16 | SQL queries taking longer than expected | Optimized queries with mentor support
Sprint 5 | Day 23 | Challenges integrating voice processing with workflows | Scheduled team debugging session
| Dummy | Dummy | Dummy | Dummy

## Retrospection
SL # Modified | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken | SL #
1 | Sprint 1 | 2024-11-04 | 2024-11-06 | Seenu Ananth | Reviewing documentation regularly | Assuming project requirements are clear | Participating in discussions and meetings | Scheduled a review session with team and mentors to clarify project goals.
2 | Sprint 3 | 2024-11-16 | 2024-11-22 | Akshaya | Prioritizing Python practice | Delaying review of tasks | Maintaining focus on coding | Achieved Python kit completion on time
3 | Sprint 4 | 2024-11-23 | 2024-11-29 | Vaibhav Sunil Shimpi | Preparing SQL practice | Rushing through SQL concepts. | Asking for help when stuck. | Completed SQL with support from the team
4 | sprint 5 | 2024-12-02 | 2024-12-06 | Vaibhav Sunil Shimpi,Seenu Ananth,Akshaya | Participating in Module 1 discussions | Delaying voice input exploration | Collaborating on language processing strategies | Completed voice input prototypes and received team feedback for improvements.
| Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy | Dummy